## Project Status Report
EMBER GROUP ¦ Development Project Status Report
| PROJECT INFORMATION | [6 empty] | KEY PROJECT MEMBERS |  |  | PROJECT DATA / METRICS
| Project Name | Shops at Grand Prairie | [5 empty] | Ember Lead | Natalia Duay |  | Total Land Area (sf) | 215839.8 |  |  | Report Date | 2026-04-22
| Project Type | Commercial / Retail | [5 empty] | Developer / Lead | HPI / Steven Tyson |  | Land Area | 4.955 |  |  | Report Period | April 2026
| Address | Betka & Kickapoo Rd | [5 empty] | General Contractor | HPI |  | Rentable SF (NRSF) | 21000 |  |  | Overall Status | Pre-Dev
| City / State | Hockley, TX | [5 empty] | Architect |  |  | Pad Sites (acres) | 2.6
| MUD District | [6 empty] | Civil Engineer | LJA |  | Efficiency (NRSF/Land) | 20.47%
| Project Structure | JV Agreement between HPI & Ember, as co-GPs | [8 empty] | Cost / NRSF | 376.0083
[11 empty] | Cost / Acre (Pad Sites) | 795679.2308
| PROJECT BUDGET | [9 empty] | PROJECT SCHEDULE
| Line Item | Original Budget | [8 empty] | Milestone | Target | Actual | Variance (Days) | Status | Notes
|  | Retail Center | Pad Sites | Total Budget | Reallocations | Adjusted Budget | Spent to Date | Balance to Finish | % Complete | Remaining Balance |  | Date | Date
| Land Acquisition | 1231005.6 | 1359072 | 2590077.6 |  | 2590077.6 |  | 2590077.6 | 0% | 2590077.6 | Execute JV Agreement | 2026-05-31 |  |  | Redlines pending
| Land Purchase Commissions | 37009 | 40694 | 77703 |  | 77703 |  | 77703 | 0% | 77703 | Land Contribution into JV agmt | 2026-06-30 |  |  |  | 30 days post agmt
| Hard Costs / GMP | 3570000 | 250000 | 3820000 |  | 3820000 |  | 3820000 | 0% | 3820000 | Kick-off Civil Engineering | 2026-05-01 |  |  | N/A
| Site Work | 225000 | 0 | 225000 |  | 225000 |  | 225000 | 0% | 225000 | Civil Plan Submittal to City for Review | 2026-07-30 |  |  |  | Assume 3 months
| TI Allowance | 1050000 | 0 | 1050000 |  | 1050000 |  | 1050000 | 0% | 1050000 | CenterPoint Easement Approval | 2026-09-30 |  |  |  | Assume 5 months
| Leasing Commissions | 399240 | 0 | 399240 |  | 399240 |  | 399240 | 0% | 399240 | Preleasing Commitments Met | 2026-08-29 |  |  |  | Assume 4 months
| Acquistion Fee (Ember) | 51802 |  | 51802 |  | 51802 |  | 51802 | 0% | 51802 | Civil plan approved by City | 2027-01-26 |  |  |  | 6 mos for review
| Title / Closing Costs | 10000 | 15000 | 25000 |  | 25000 |  | 25000 | 0% | 25000 | Permits received | 2027-02-01
| Due Diligence Reports | 30000 | 45000 | 75000 |  | 75000 |  | 75000 | 0% | 75000 | Construction Loan Closing | 2027-02-02
| Permit & Impact Fees | 250000 | 35000 | 285000 |  | 285000 |  | 285000 | 0% | 285000 | NTP - Commence site work | 2027-02-11
| Architectural & Engineering | 150000 | 60000 | 210000 |  | 210000 |  | 210000 | 0% | 210000 | Construction Completion | 2028-02-06 |  |  |  | Assume 12 months
| Legal | 35000 | 25000 | 60000 |  | 60000 |  | 60000 | 0% | 60000
| Marketing | 5000 |  | 5000 |  | 5000 |  | 5000 | 0% | 5000 | Leasing & Marketing
| Signage | 50000 | 25000 | 75000 |  | 75000 |  | 75000 | 0% | 75000 | Marketing Pkg goes Live @ ICSC | 2026-05-18
| Property Taxes | 50000 | 50000 | 100000 |  | 100000 |  | 100000 | 0% | 100000 | C-store & Pad Site Commitments/PSA | 2026-08-16 |  |  |  | Assume 90 days
| Lender Fees & Closing Costs | 73749 |  | 73749 |  | 73749 |  | 73749 | 0% | 73749 | Pre-leasing met for Lender | 2026-09-15 |  |  |  | Assume 120 days
| Interest Reserve | 286648 |  | 286648 |  | 286648 |  | 286648 | 0% | 286648
| Operating Reserves | 116720 |  | 116720 |  | 116720 |  | 116720 | 0% | 116720
| Contingency | 125000 | 100000 | 225000 |  | 225000 |  | 225000 | 0% | 225000
| Development Fee | 150000 | 64000 | 214000 |  | 214000 |  | 214000 | 0% | 214000
| TOTAL PROJECT BUDGET | 7896173.6 | 2068766 | 9964939.6 | 0 | 9964939.6 | 0 | 9964939.6 | 0% | 9964939.6 | GMP BUYOUT ANALYSIS
| CONTINGENCY & RISK TRACKER | [9 empty] | Description | Original GMP | Change Orders | Adjusted GMP | Committed | % Bought Out
| Risk Category | Potential Issue | Impact Description |  |  | Hard Cost ($) | Soft Cost ($) | Probability | Weighted Exposure | Status | Sitework / Civil |  |  | 0 |  | 0%
| Beginning Contingency |  |  |  |  | 225000 |  |  |  |  | Concrete / Foundations |  |  | 0 |  | 0%
| Permitting | [7 empty] | 0 |  | Structural Steel / Framing |  |  | 0 |  | 0%
| Financial / Market | [7 empty] | 0 |  | Roofing & Waterproofing |  |  | 0 |  | 0%
| Environmental / Geotech | [7 empty] | 0 |  | MEP (Mech / Elec / Plumbing) |  |  | 0 |  | 0%
| Labor / Material Escalation | [7 empty] | 0 |  | Finishes / Interiors |  |  | 0 |  | 0%
| Design Changes | [7 empty] | 0 |  | General Conditions & Fee |  |  | 0 |  | 0%
| Projected Contingency Balance |  |  |  |  | 225000 | 0 |  | 0 |  | TOTAL GMP | 0 | 0 | 0 | 0 | 0%
| CHANGE ORDER LOG | [9 empty] | TENANT / LEASE-UP TRACKER
| CO # | Description | Amount |  |  | Source of Funds | Submitted | Approved? | Date Approved | Running Total | Tenant / Pad | Suite / Pad # | Rentable SF | Lease Status | Est. Rent (NNN) | Target Open
| 1 | [8 empty] | 0
| 2 | [8 empty] | 0
| 3 | [8 empty] | 0
| 4 | [8 empty] | 0
| 5 | [8 empty] | 0
| TOTAL CHANGE ORDERS |  | 0 | [6 empty] | 0 | TOTAL LEASED |  | 0
| UPCOMING MILESTONES & ACTION ITEMS | [9 empty] | ISSUES & CONCERNS
| # | Item Descr. | Details |  |  | Target Date | Priority | Status |  |  | # | Issue Description | Impact | Action Plan | Owner | Target Resolution
| 1 | LP IRR calcs | Adj waterfall / deal structure with earlier land contri. |  |  | 2026-04-26 | Yes | Pending Internal Discussion with Partners |  |  | 1 | Timing of Land contribution | LP IRR; Agmts getting finalized | Waiting on approval from partners | Natalia | 2026-04-26
| 2 | Company Agmts | Execute Proj Entity & GP Agmt |  |  | 2026-05-15 | Yes | Waiting on land contribution decision before sending comments back |  |  | 2
| 3 | [9 empty] | 3
| 4 | [9 empty] | 4
| 5 | [9 empty] | 5
CONSTRUCTION PHOTOS / SITE PROGRESS
| [ Insert Photo 1 ] | [9 empty] | [ Insert Photo 2 ]
Ember Group ¦ Confidential ¦ For Internal Use Only
Formulas:
Target = [Target, row above]+30